## Dashboard
BIDSHIELD IMPLEMENTATION DASHBOARD
Total Items | Done | In Progress | Not Started | Critical Open | Total Hours
63 | 2 | 0 | 61 | 12 | 264
BY SEVERITY
Severity | Total | Done | Remaining | % Complete
CRITICAL | 14 | 2 | 12 | 14.29%
HIGH | 25 | 0 | 25 | 0%
MEDIUM | 24 | 0 | 24 | 0%
BY SPRINT
Sprint | Items | Done | Hours | % Complete
Sprint 0 (Now) | 5 | 2 | 5 | 40%
Sprint 1 | 19 | 0 | 69 | 0%
Sprint 2 | 13 | 0 | 93 | 0%
Sprint 3 | 18 | 0 | 65 | 0%
Sprint 4 | 4 | 0 | 16 | 0%
Backlog | 4 | 0 | 16 | 0%

## Fix Tracker
BIDSHIELD MASTER FIX TRACKER
All audit findings + AI roadmap items ¦ Updated April 2026
ID | Finding | Component/Tab | Severity | Status | Sprint | Effort (hrs) | Depends On | Fix Description | Files to Change | Notes
S1 | Exposed secrets in version control | Security | CRITICAL | Not Started | Sprint 0 (Now) | 1 | None | Remove .env files from git history, rotate ALL keys (Clerk, Anthropic, Stripe, HeyGen), add .env* to .gitignore | .env.local, .env.production.local, .gitignore | DONE if already rotated — verify
S2 | Duplicate Stripe webhook endpoints | Security | CRITICAL | Not Started | Sprint 0 (Now) | 2 | None | Consolidate to single webhook handler, remove duplicate endpoint, verify Stripe dashboard has one URL | api/bidshield/webhook, api/webhooks/stripe | Check Stripe dashboard
C1 | Zero test coverage → 259 tests added | Testing | CRITICAL | Done | Sprint 0 (Now) | 0 | None | COMPLETED: 9 test files, 259 tests covering roundCurrency, bidScore, scopePricingConflicts, utils, rateLimit, checklist-data, material-templates, scope-defaults | __tests__/* | DONE — keep expanding
M1 | 3,098-line monolith split into modules | Maintainability | CRITICAL | Done | Sprint 0 (Now) | 0 | None | COMPLETED: Split into 21 module files under convex/bidshield/ with re-exports maintaining API compatibility | convex/bidshield.ts, convex/bidshield/* | DONE — deployed to Convex
E-04 | No critical-phase enforcement at submission | Checklist | CRITICAL | Not Started | Sprint 1 | 4 | E-26 | Add phase completion gates: require Scope Boundaries, Pricing, Labor phases > 80% before submission is enabled | convex/bidshield/checklist.ts, SubmissionTab or Validator
E-06 | No scope-to-pricing flow | Scope | CRITICAL | Not Started | Sprint 2 | 8 | None | When scope items marked 'included', auto-create pricing line items. Add sync mutation that reads scope status and creates/updates pricing entries | convex/bidshield/scope.ts, PricingTab.tsx | Core tab-sync issue
E-09 | Addendum price impact not linked to Pricing | Addenda | CRITICAL | Not Started | Sprint 2 | 6 | E-06 | Wire addendum price impacts to the actual bid total. When addendum flags +$4,500, that should flow into pricing as an adjustment line item | convex/bidshield/addenda.ts, pricing logic
E-13 | Takeoff quantities don't flow to Materials | Takeoff | CRITICAL | Not Started | Sprint 2 | 8 | None | Create sync: takeoff total SF/LF/EA per section → material quantity calculation using coverage rates. This is the #1 workflow gap | convex/bidshield/takeoff.ts, materials.ts, MaterialsTab.tsx | Biggest estimator pain point
E-19 | Labor total not synced to Pricing | Labor | CRITICAL | Not Started | Sprint 2 | 4 | None | Single source of truth: labor tab calculates total → pricing tab reads it. Remove independent laborCost field from pricing or make it read-only computed | convex/bidshield/labor.ts, PricingTab.tsx | Conflicting numbers = bid errors
E-26 | Validator doesn't block submission | Validator | CRITICAL | Not Started | Sprint 1 | 4 | None | Add submission gate: if bid score < threshold (configurable, default 85%), disable submit button with clear message showing what needs fixing | SubmissionTab.tsx, convex/bidshield/submissions.ts
E-27 | Component reconciliation is advisory only | Validator | CRITICAL | Not Started | Sprint 1 | 6 | E-26 | Make reconciliation blocking: if Material + Labor + GC differs from Total Bid by > 2%, require estimator acknowledgment before submission | Validator logic, SubmissionTab.tsx
S3 | CSP allows unsafe-inline/unsafe-eval | Security | HIGH | Not Started | Sprint 1 | 3 | None | Tighten Content-Security-Policy in vercel.json: remove unsafe-inline, add nonce-based script loading | vercel.json, next.config.js
S4 | Unauthenticated checkout endpoints | Security | HIGH | Not Started | Sprint 0 (Now) | 2 | None | Add Clerk auth check to checkout API routes. Reject requests without valid session | api/checkout/* | Revenue protection
S5 | Missing CSRF protection on mutations | Security | HIGH | Not Started | Sprint 1 | 4 | None | Add CSRF token validation to all POST endpoints in api/bidshield/* | api/bidshield/*, middleware
P1 | N+1 RFI queries in getStats | Performance | HIGH | Not Started | Sprint 1 | 2 | M1 | Batch RFI count query: single query with projectId filter instead of per-project loop | convex/bidshield/stats.ts | DONE if module split fixed this — verify
C2 | Floating-point arithmetic in pricing | Correctness | HIGH | Not Started | Sprint 1 | 3 | None | Apply roundCurrency() to all financial calculations. Helper already exists in _helpers.ts | convex/bidshield/_helpers.ts, materials.ts, labor.ts, pricing logic | roundCurrency built
E-01 | Assembly areas don't validate against gross roof area | Setup | HIGH | Not Started | Sprint 1 | 2 | None | Add validation: sum of assembly areas vs gross roof area. Show warning banner if delta > 5% | SetupTab.tsx
E-07 | No bulk status operations for scope | Scope | HIGH | Not Started | Sprint 3 | 3 | None | Add multi-select + bulk status change (mark 5 items 'by_others' at once) | ScopeTab.tsx, convex/bidshield/scope.ts
E-10 | No 'Go Reprice' action from addendum | Addenda | HIGH | Not Started | Sprint 3 | 2 | E-09 | Add button on addendum items that navigates to the affected pricing/material line item | AddendaTab.tsx | UX improvement
E-11 | No RFI response deadline tracking | RFIs | HIGH | Not Started | Sprint 3 | 3 | None | Add responseDeadline field, show overdue RFIs with visual indicator, optional notification | convex/bidshield/rfis.ts, RFIsTab.tsx
E-14 | No reconciliation between section areas and gross roof area | Takeoff | HIGH | Not Started | Sprint 2 | 2 | E-13 | Show running total of takeoff areas vs gross area with visual delta indicator | TakeoffTab.tsx
E-16 | Quote-to-material matching is manual | Materials | HIGH | Not Started | Sprint 2 | 4 | None | Auto-run fuzzy matching when new quote is added. Show match confidence. Already have matching logic — need to trigger it automatically | MaterialsTab.tsx, quote matching logic | Fuzzy matching exists at 70% threshold
E-17 | No waste factor validation | Materials | HIGH | Not Started | Sprint 1 | 2 | None | Add range validation: warn if waste < 3% or > 25%. Show industry standard ranges by category | MaterialsTab.tsx, convex/bidshield/materials.ts
E-20 | AI labor assumptions not actionable | Labor | HIGH | Not Started | Sprint 3 | 4 | None | Add drill-down: click AI assumption → see calculation breakdown, edit individual factors | LaborTab.tsx
E-21 | Unverified labor tasks don't block submission | Labor | HIGH | Not Started | Sprint 2 | 2 | E-26 | Add 'verified' checkbox per labor task. Unverified AI tasks count against bid score | LaborTab.tsx, convex/bidshield/labor.ts
E-24 | PDF extraction failure is silent | Quotes | HIGH | Not Started | Sprint 1 | 2 | None | Show clear error toast when PDF extraction returns empty or fails. Offer manual entry fallback | MaterialsTab.tsx, QuotesTab.tsx
E-28 | Score doesn't weight critical phases | Validator | HIGH | Not Started | Sprint 2 | 3 | E-26 | Add weighted scoring: Scope/Pricing/Labor/Quotes phases worth 2x. Adjust bid score formula | lib/bidshield/bid-score.ts
E-30 | Decision Log has no UI entry points | Cross-Cutting | HIGH | Not Started | Sprint 3 | 3 | None | Add 'Log Decision' button accessible from all tabs. Quick-entry modal for logging rationale | DecisionLog component, all tabs
E-31 | No audit trail for bid amount changes | Cross-Cutting | HIGH | Not Started | Sprint 3 | 4 | None | Log every bid total change with timestamp, old value, new value, source (which tab/action caused it) | convex/bidshield/decisions.ts or new audit table
E-33 | No CSV/Excel export from analytics | Analytics | HIGH | Not Started | Sprint 4 | 3 | None | Add export buttons on analytics dashboard. CSV for data, PDF for reports | AnalyticsTab.tsx
E-34 | PDF export is bid-day reference only | Analytics | HIGH | Not Started | Sprint 4 | 6 | None | Expand PDF export to full bid package: cover sheet, scope, material list, pricing breakdown, exclusions, qualifications | PDF generation logic
P2 | Sequential deletes in deleteProject | Performance | MEDIUM | Not Started | Sprint 3 | 2 | None | Use Promise.all for parallel deletes across tables | convex/bidshield/projects.ts
P3 | Full table scan in quote upserting | Performance | MEDIUM | Not Started | Sprint 3 | 3 | P5 | Use compound index lookup instead of loading all datasheets for fuzzy match | convex/bidshield/datasheets.ts
P4 | Waterfall query loading on dashboard | Performance | MEDIUM | Not Started | Sprint 3 | 2 | None | Combine sequential useQuery calls or use Convex's query batching | BidQualsTab.tsx
P5 | Missing compound database indexes | Performance | MEDIUM | Not Started | Sprint 1 | 1 | None | PARTIALLY DONE: Added 3 indexes in module split. Review remaining query patterns for missing indexes | convex/schema.ts | 3 indexes added — check for more
C3 | Race condition in labor task updates | Correctness | MEDIUM | Not Started | Sprint 3 | 3 | None | Use optimistic concurrency: include version field, reject updates with stale version | convex/bidshield/labor.ts
C4 | Webhook duplicate processing risk | Correctness | MEDIUM | Not Started | Sprint 1 | 2 | S2 | Add idempotency key tracking: store processed Stripe event IDs, skip duplicates | api/webhooks/stripe/route.ts
C5 | JSON.parse without try-catch | Correctness | MEDIUM | Not Started | Sprint 1 | 1 | None | Wrap all JSON.parse calls in try-catch with graceful fallbacks | api/download, checkout, webhooks | Quick fix
M2 | Code duplication across mutations | Maintainability | MEDIUM | Not Started | Sprint 3 | 3 | M1 | Extract shared validation and insert patterns into _helpers.ts | convex/bidshield/_helpers.ts | Module split makes this easier
M3 | Missing numeric field validation | Maintainability | MEDIUM | Not Started | Sprint 2 | 2 | None | Add range validators: wasteFactor 1.0-1.5, ratePerUnit > 0, quantity >= 0 | convex/bidshield/materials.ts, labor.ts
M4 | Hardcoded configuration values | Maintainability | MEDIUM | Not Started | Backlog | 2 | None | Move rate limits, labor multipliers, API versions to config file or environment variables | lib/rateLimit.ts, API routes | Low urgency
M5 | Missing inline documentation | Maintainability | MEDIUM | Not Started | Backlog | 4 | None | Add JSDoc to all exported functions, document financial algorithms | All backend files | Ongoing
E-02 | No assembly deletion confirmation | Setup | MEDIUM | Not Started | Sprint 1 | 1 | None | Add confirm dialog before deleting an assembly | SetupTab.tsx | Quick fix
E-03 | R-value lookup fails silently | Setup | MEDIUM | Not Started | Sprint 1 | 1 | None | Show toast or inline message when R-value calculation fails | SetupTab.tsx | Quick fix
E-05 | Template save failure is silent | Checklist | MEDIUM | Not Started | Sprint 1 | 1 | None | Show error toast when checklist template save fails | ChecklistTab.tsx | Quick fix
E-08 | Excluded item cost not displayed | Scope | MEDIUM | Not Started | Sprint 3 | 2 | E-06 | Show excluded items with their estimated cost impact (what you're NOT including) | ScopeTab.tsx
E-12 | Answered RFIs can't be reopened | RFIs | MEDIUM | Not Started | Sprint 3 | 1 | None | Add 'Reopen' button on answered RFIs with reason field | RFIsTab.tsx, convex/bidshield/rfis.ts
E-15 | Line item verification has no downstream effect | Takeoff | MEDIUM | Not Started | Sprint 3 | 2 | E-13 | Verified takeoff items contribute to bid score. Unverified items flag as risk | TakeoffTab.tsx, bid-score.ts
E-18 | No material-to-bid reconciliation | Materials | MEDIUM | Not Started | Sprint 2 | 2 | E-13 | Show material total vs bid's material line with delta indicator | MaterialsTab.tsx, pricing view
E-22 | Markup calculation order is opaque | General Conditions | MEDIUM | Not Started | Sprint 3 | 2 | None | Show markup calculation breakdown: base cost → overhead → profit → bond → tax with running subtotal | PricingTab or GC tab
E-23 | No frozen base for change orders | General Conditions | MEDIUM | Not Started | Sprint 4 | 3 | None | Add 'freeze bid base' action that locks current totals, tracks subsequent changes as deltas | convex/bidshield/projects.ts
E-25 | Expired quotes remain visible | Quotes | MEDIUM | Not Started | Sprint 3 | 2 | None | Add visual indicator for expired quotes, option to archive. Filter by active/expired | QuotesTab.tsx
E-29 | No integration with actual submission | Submission | MEDIUM | Not Started | Backlog | 8 | None | Future: integrate with GC submission portals or email-based submission | New integration layer | Long-term
E-32 | Demo mode inconsistency | Cross-Cutting | MEDIUM | Not Started | Backlog | 2 | None | Ensure demo data follows same code paths as production data | Demo data generation
E-35 | No bid accuracy drill-down | Analytics | MEDIUM | Not Started | Sprint 4 | 4 | None | Post-award: compare bid line items vs actual costs. Track accuracy by category over time | Analytics system
AI-01 | Spec Extraction Endpoint (extract-specifications) | AI Pipeline | CRITICAL | Not Started | Sprint 1 | 20 | None | New endpoint: reads multiple roofing spec PDFs, extracts materials + warranties + installation reqs + testing reqs + submittals. Supports multiple spec sections (07 52 00, 07 22 00, etc.) | NEW: api/bidshield/extract-specifications/route.ts | Phase 1A — foundation for everything
AI-02 | Spec Requirements Database Table | AI Pipeline | CRITICAL | Not Started | Sprint 1 | 4 | None | New Convex table bidshield_spec_requirements: stores extracted spec data by type (material/warranty/installation/testing/submittal). Indexes: by_project, by_project_section, by_project_type. Links to price library via linkedDatasheetId | NEW: convex/schema.ts, convex/bidshield/specRequirements.ts | Phase 1C — do first
AI-03 | Spec Material Dashboard UI | AI Pipeline | CRITICAL | Not Started | Sprint 2 | 20 | AI-01, AI-02 | New tab/panel showing all spec-extracted requirements. Columns: material + manufacturer, spec section, coverage rate, current price (from price library), price expiration, quantity (from EDGE), extended cost. Warranty panel. Submittal tracker. | NEW: SpecDashboardTab.tsx or panel | Phase 1B — replaces manual spec reading
AI-04 | Zoning Drawing Area Auto-Populate | AI Pipeline | HIGH | Not Started | Sprint 1 | 6 | None | Enhance extract-assemblies prompt to prioritize area schedule pages from zoning drawings. Return areas in assembly objects → auto-fill Setup Tab | api/bidshield/extract-assemblies/route.ts | Phase 2A — mostly prompt tuning
AI-05 | Wizard Post-Creation Auto-Init | Wizard | HIGH | Not Started | Sprint 2 | 8 | None | After wizard creates project, auto-initialize: materials (from templates by system type), scope items (from trade template), takeoff sections (per assembly label). Currently requires manual init from each tab. | app/bidshield/dashboard/page.tsx, convex/bidshield/projects.ts | Phase 2B
AI-06 | GC Exhibit A Pricing Checklist | AI Pipeline | HIGH | Not Started | Sprint 3 | 12 | None | Enhance extract-gc-form: add 'pricing-line-item' itemType for Exhibit A pricing schedules. Extract line descriptions, units, quantities. Auto-match against project scope and materials. New UI panel for pricing checklist. | api/bidshield/extract-gc-form/route.ts, GCItemsTab.tsx | Phase 3A
AI-07 | EDGE Quantity Comparison Dashboard | AI Pipeline | HIGH | Not Started | Sprint 3 | 12 | AI-03 | Compare BidShield-calculated quantities vs EDGE report quantities (same materials, different quantities). Flag items where variance > 5%. Dashboard: material ¦ EDGE qty ¦ BidShield qty ¦ variance % ¦ status | NEW: quantity comparison component | Phase 4A
AI-08 | Tab Cross-Communication Wiring | Architecture | HIGH | Not Started | Sprint 2 | 24 | E-13, E-19 | Wire up all tab data flows: Takeoff→Materials (quantities), Materials→Pricing (costs), Labor→Pricing (hours×rates), Setup→Takeoff (areas), Spec Dashboard→Materials (requirements), Price Library→Materials (pricing) | Multiple convex mutations + tab components | Phase 4B — depends on critical fixes
TOTALS | [5 empty] | 264

## Sprint Plan
SPRINT BREAKDOWN
Sprint | Focus | Key Deliverables | Est. Hours | Dependencies | Go-Live Risk
Sprint 0 (NOW) | Security + Already Done | S1: Rotate exposed secrets S2: Fix duplicate webhooks S4: Auth checkout endpoints C1: 259 tests (DONE) M1: Module split (DONE) Assembly wizard fix (DONE) | 5 | None | ZERO
Sprint 1 (Week 1-2) | Foundation + Guardrails | AI-02: Spec requirements DB table AI-01: extract-specifications endpoint AI-04: Zoning area auto-populate E-26: Submission threshold gate E-27: Component reconciliation blocking E-04: Critical phase enforcement Quick fixes: E-02, E-03, E-05, C5, P5, E-17, E-24 | ~52 | None | LOW New features only
Sprint 2 (Week 3-4) | Tab Sync + Spec Dashboard | AI-03: Spec Material Dashboard UI AI-05: Wizard post-creation auto-init AI-08: Tab cross-communication wiring E-13: Takeoff → Materials flow (CRITICAL) E-19: Labor → Pricing sync (CRITICAL) E-06: Scope → Pricing flow E-09: Addendum → Pricing link | ~80 | Sprint 1 endpoints | LOW-MED New connections
Sprint 3 (Week 5-6) | GC Processing + Polish | AI-06: GC Exhibit A pricing checklist AI-07: EDGE quantity comparison E-07: Bulk scope operations E-10, E-11: Addenda/RFI improvements E-20, E-30, E-31: Labor/Decision UX Performance: P2, P3, P4, C3 | ~60 | Sprint 2 tab sync | LOW Enhancements
Sprint 4 (Week 7-8) | Analytics + Export | E-33: CSV/Excel export E-34: Full bid package PDF E-23: Frozen base for change orders E-35: Bid accuracy drill-down M4, M5: Config cleanup + docs | ~30 | None | ZERO Reporting only
Backlog | Future / Low Priority | E-29: GC portal integration E-32: Demo mode cleanup M4: Hardcoded config values M5: Inline documentation | ~16 | None | ZERO

## Deploy Strategy
DEPLOYMENT STRATEGY — SAFE UPDATES ON A LIVE SITE
Vercel (frontend) + Convex (backend) ¦ Auto-deploy from git push
1. GIT BRANCHING STRATEGY
Branch | Purpose | Deploys To | Who Pushes | Auto-Deploy? | Notes
main | Production code — what users see | Vercel Production + Convex Production | Merge PRs only | YES | NEVER push directly. Always merge from dev via PR
dev | Integration branch — all features merge here first | Vercel Preview URL | You | YES | Test everything here before merging to main
feature/* | Individual fixes (feature/fix-e13-takeoff-sync) | Vercel Preview URL | You | YES | One branch per fix or feature. Branch from dev
hotfix/* | Emergency production fixes only | Vercel Production (fast-track) | You | After merge to main | Branch from main, merge to BOTH main and dev
2. PRE-DEPLOY CHECKLIST (before every merge to main)
Step | Action | Command / How | If It Fails | Required? | Notes
1 | Run all tests | npm run test | Fix failing tests before proceeding | YES | 259 tests must pass
2 | TypeScript type check | npx tsc --noEmit | Fix type errors | YES | Catches null/undefined bugs
3 | Build locally | npm run build | Fix build errors | YES | Catches import issues
4 | Test Convex functions | npx convex dev (check console) | Fix Convex validation errors | YES | Catches schema mismatches
5 | Preview deploy (Vercel) | Push to dev branch → check preview URL | Fix in feature branch, re-push | YES | Vercel auto-creates preview
6 | Manual smoke test | Open preview URL, create project, upload PDF, check all tabs | Fix issues found | YES | 5-min walkthrough of core flow
7 | Deploy Convex production | npx convex deploy | Check error, fix schema/function issues | YES | BEFORE merging to main if schema changed
8 | Merge to main | PR from dev → main on GitHub | Revert if Vercel deploy fails | YES | Triggers Vercel production deploy
9 | Post-deploy verify | Check production URL, verify core flow works | Revert: git revert HEAD on main | YES | 2-min smoke test on live site
3. CONVEX DEPLOYMENT — CRITICAL GOTCHAS
Scenario | What Happens | Safe Approach | Danger Level
Adding new table | No risk — existing data untouched | Just add to schema.ts and deploy | SAFE
Adding new field to existing table | Old rows won't have the field | Use v.optional() for new fields. Code must handle undefined | LOW
Removing a field from schema | Existing data still has the field but schema rejects it | DON'T remove fields — mark as deprecated with v.optional(). Remove data first if needed | HIGH
Renaming a table | Old table deleted, new one empty | Create new table, migrate data, then remove old table in separate deploy | CRITICAL
Adding a new index | Index builds in background | Safe — just deploy. May take a few seconds for large tables | SAFE
Changing a field type (e.g., string → number) | Existing data has old type, new code expects new type | Add new field with new type, migrate data, remove old field later | CRITICAL
Frontend + Convex schema change together | If Vercel deploys before Convex, frontend calls fail | Deploy Convex FIRST (npx convex deploy), THEN merge to main for Vercel | HIGH
4. ROLLBACK PROCEDURES — WHEN THINGS GO WRONG
Problem | How You'll Know | Fix | Time to Fix
Vercel deploy broke the site | Preview URL shows error or blank page | Go to Vercel dashboard → Deployments → click '...' on previous deploy → 'Promote to Production'. Instant rollback. | 30 seconds
Convex function errors after deploy | Users see errors, Convex dashboard shows function failures | Run: npx convex deploy --cmd 'git stash' from the last working commit. Or revert git commit and redeploy. | 2-5 minutes
Schema migration broke data | Convex dashboard shows validation errors on existing documents | Fix schema to be backward-compatible (add v.optional). Never remove fields from live tables. | 5-10 minutes
Both frontend + backend broken | Nothing works | 1. Vercel: promote previous deploy. 2. Convex: redeploy from previous commit. 3. Fix in feature branch. | 5-10 minutes
Stripe webhooks failing | Stripe dashboard shows failed webhook deliveries | Check Stripe webhook logs for error details. Fix handler. Stripe auto-retries for up to 72 hours. | Varies